## Sheet
Task Number | Interval rounded down | Men Modified | M/H Modified
062000-00-01 | 1 | 1 | 0.3 | This is the list used as input for the python code. Compared to the modified MPD, is this sheet the intervals have been adjusted so that most intervals are a multiple of 37 days. This has been done to reduce the hangar days and thereby the cost of maintenance.
261100-00-01 | 1 | 1 | 0.1
261200-00-01 | 1 | 1 | 0.1
261303-00-01 | 1 | 1 | 0.1
321100-00-09 | 1 | 1 | 0.1
321100-00-09 | 1 | 1 | 0.1
324100-00-02 | 1 | 1 | 0.3
324100-00-03 | 1 | 1 | 0.2 | Hangar days have been determined by the type of tasks. We found that, tasks with an interval below 18 days** are only visual, functional or operational inspections which can be performed on the apron. Wherass tasks above the 18 days interval included replacement of equipment or in-depth inspections.
324200-00-02 | 1 | 1 | 0.2
351100-00-03 | 1 | 1 | 0.1
723500-00-01 | 1 | 1 | 0.1
761100-00-01 | 1 | 1 | 0.1
281400-01-04 | 2 | 1 | 0.4
241000-00-01 | 4 | 1 | 0.2
241000-00-01 | 4 | 1 | 0.2
291300-00-01 | 4 | 1 | 0.2 | **: The intervals have been calculated by using the FH, FC, AH, DAILY, MO, YR and we used our flightplan of 13.5 hours for this. To see how exactly we calculated this, see the modified MPD.
212900-00-01 | 9 | 1 | 0.1
242000-00-01 | 9 | 2 | 0.1
242000-02-01 | 9 | 2 | 0.1
243000-00-03 | 9 | 1 | 0.2
261100-01-01 | 9 | 1 | 0.1
261200-01-01 | 9 | 1 | 0.1
335000-00-03 | 11 | 1 | 0.1
523300-00-09 | 11 | 1 | 0.2
215000-00-01 | 18 | 1 | 0.2
261303-01-01 | 18 | 1 | 0.1
273500-00-03 | 18 | 1 | 0.1
221100-50-01 | 18 | 1 | 0.8
262400-00-01 | 18 | 1 | 0.1
291200-00-01 | 18 | 1 | 0.2
304100-01-01 | 18 | 1 | 0.1
524504-50-01 | 18 | 1 | 0.1
212000-00-02 | 37 | 1 | 0.6
212630-00-02 | 37 | 1 | 0.1
271300-00-02 | 37 | 1 | 0.1
273200-00-02 | 37 | 1 | 0.1
274300-00-02 | 37 | 1 | 0.1
291300-00-04 | 37 | 1 | 0.2
291300-00-05 | 37 | 1 | 0.2
291300-00-06 | 37 | 1 | 0.2
291300-00-07 | 37 | 1 | 0.1
360000-00-16 | 37 | 1 | 1.1
360000-00-16 | 37 | 1 | 1.1
360000-00-17 | 37 | 1 | 1.1
360000-00-17 | 37 | 1 | 1.1
527100-00-02 | 37 | 1 | 0.1
212630-00-01 | 37 | 1 | 0.1
215000-00-12 | 37 | 1 | 0.1
256102-00-01 | 37 | 1 | 0.1
256102-00-01 | 37 | 1 | 0.1
256102-00-01 | 37 | 1 | 0.1
256202-00-01 | 37 | 1 | 0.1
256202-00-02 | 37 | 1 | 0.1
262400-00-03 | 37 | 1 | 0.1
274200-01-13 | 37 | 1 | 0.2
276400-00-03 | 37 | 1 | 0.2
281400-01-05 | 37 | 1 | 0.4
281400-01-06 | 37 | 1 | 2.1
281400-01-07 | 37 | 1 | 4
291100-00-01 | 37 | 1 | 0.2
291100-00-03 | 37 | 1 | 0.2
291100-00-04 | 37 | 1 | 0.2
314100-00-01 | 37 | 1 | 0.1
324400-00-04 | 37 | 1 | 0.2
324500-00-03 | 37 | 1 | 0.2
360000-00-15 | 37 | 1 | 0.1
740000-00-01 | 37 | 2 | 0.2
740000-02-01 | 37 | 1 | 0.2
774700-00-01 | 37 | 1 | 0.3
774700-00-01 | 37 | 1 | 0.3
275300-00-05 | 37 | 1 | 1.8
275300-00-05 | 37 | 1 | 1.8
215000-50-03 | 37 | 1 | 2.2
321100-03-09 | 37 | 1 | 0.1
321100-03-09 | 37 | 1 | 0.1
062403-00-01 | 74 | 1 | 0.6
062403-00-01 | 74 | 1 | 0.6
215000-00-09 | 74 | 1 | 0.1
241000-00-02 | 74 | 1 | 0.4
241000-00-02 | 74 | 1 | 0.4
254201-00-01 | 74 | 1 | 0.3
255100-00-01 | 74 | 1 | 0.3
273500-00-01 | 74 | 1 | 0.2
491000-00-02 | 74 | 1 | 0.4
725200-00-02 | 74 | 1 | 0.1
725200-00-02 | 74 | 1 | 0.1
730000-00-06 | 74 | 1 | 1
753200-00-02 | 74 | 1 | 1.1
753200-00-02 | 74 | 1 | 1.1
762000-00-01 | 74 | 2 | 0.3
762300-00-02 | 74 | 1 | 0.2
762300-00-02 | 74 | 1 | 0.2
773100-00-01 | 74 | 1 | 0.2
274300-01-04 | 74 | 1 | 0.3
315100-00-01 | 74 | 1 | 0.1
341600-00-02 | 74 | 1 | 0.1
351100-00-06 | 74 | 1 | 0.1
725200-00-01 | 74 | 1 | 0.2
725200-00-01 | 74 | 1 | 0.2
725300-00-01 | 74 | 1 | 0.2
725300-00-01 | 74 | 1 | 0.2
730000-00-04 | 74 | 1 | 0.1
275300-00-07 | 74 | 1 | 1.4
275300-00-07 | 74 | 1 | 1.4
276400-00-02 | 74 | 1 | 1.1
523003-00-01 | 74 | 1 | 0.3
321100-00-15 | 74 | 1 | 2
321100-00-15 | 74 | 1 | 2
353100-00-02 | 74 | 1 | 0.1
212000-02-03 | 111 | 1 | 0.6
730000-00-01 | 111 | 1 | 0.4
730000-00-01 | 111 | 1 | 0.4
353103-00-01 | 111 | 1 | 0.1
499000-00-01 | 111 | 1 | 0.2
499000-00-02 | 111 | 1 | 0.2
212000-00-03 | 148 | 1 | 1.3
274200-00-06 | 148 | 1 | 0.5
301100-00-01 | 148 | 1 | 0.1
301200-00-01 | 148 | 1 | 0.1
491000-02-02 | 148 | 1 | 0.4
753200-00-04 | 148 | 1 | 0.6
753200-00-04 | 148 | 1 | 0.6
753200-00-05 | 148 | 1 | 0.6
753200-00-05 | 148 | 1 | 0.6
753200-00-06 | 148 | 1 | 0.6
753200-00-06 | 148 | 1 | 0.6
523051-00-03 | 148 | 1 | 0.3
533014-00-03 | 148 | 1 | 0.3
322201-00-03 | 148 | 1 | 0.1
212300-00-02 | 177 | 1 | 0.1
215000-00-03 | 177 | 1 | 2.8
237100-00-02 | 177 | 1 | 0.1
255201-00-01 | 177 | 1 | 0.2
255201-00-01 | 177 | 1 | 0.2
321201-00-03 | 177 | 1 | 0.2
321201-00-03 | 177 | 1 | 0.2
360000-05-18 | 177 | 1 | 0.4
360000-05-18 | 177 | 1 | 0.4
360000-05-19 | 177 | 1 | 0.4
360000-05-19 | 177 | 1 | 0.4
723500-00-05 | 177 | 1 | 0.2
723500-00-05 | 177 | 1 | 0.2
774400-00-03 | 177 | 1 | 0.2
774400-00-03 | 177 | 1 | 0.2
521151-00-01 | 177 | 1 | 0.2
521251-00-01 | 177 | 1 | 0.2
523051-00-02 | 177 | 1 | 0.3
523351-00-03 | 177 | 1 | 0.2
524151-00-01 | 177 | 1 | 0.1
524551-00-01 | 177 | 1 | 0.1
531030-00-02 | 177 | 1 | 0.1
531031-00-02 | 177 | 1 | 0.1
533002-00-02 | 177 | 1 | 0.1
533014-00-01 | 177 | 1 | 0.2
533027-00-01 | 177 | 1 | 0.2
533027-01-01 | 177 | 1 | 0.1
533029-00-02 | 177 | 1 | 0.1
533029-01-02 | 177 | 1 | 0.1
534110-00-02 | 177 | 1 | 0.3
534116-00-01 | 177 | 1 | 0.2
534125-00-01 | 177 | 1 | 0.1
521202-01-09 | 177 | 1 | 0.1
212000-01-03 | 222 | 1 | 0.6
215000-00-08 | 222 | 2 | 13
236000-00-03 | 222 | 1 | 0.4
236000-00-03 | 222 | 1 | 3.8
236000-00-03 | 222 | 1 | 0.1
236000-00-03 | 222 | 1 | 0.1
256600-00-01 | 222 | 1 | 0.1
274100-00-06 | 222 | 1 | 1.2
302000-00-04 | 222 | 1 | 0.3
321201-00-02 | 222 | 1 | 0.1
321201-00-02 | 222 | 1 | 0.1
323200-00-02 | 222 | 1 | 0.1
323200-00-02 | 222 | 1 | 0.1
521103-01-08 | 222 | 1 | 0.3
521202-00-08 | 222 | 1 | 0.1
525100-00-03 | 222 | 1 | 0.2
215000-50-02 | 222 | 1 | 4.4
062304-00-01 | 259 | 1 | 0.4
243000-00-01 | 259 | 1 | 0.1
255700-00-02 | 259 | 1 | 0.2
273500-03-01 | 259 | 1 | 0.5
273500-03-08 | 259 | 1 | 0.3
274200-01-02 | 259 | 1 | 0.2
274200-01-08 | 259 | 1 | 0.3
274400-01-01 | 259 | 1 | 0.1
360000-00-23 | 259 | 1 | 0.4
360000-00-23 | 259 | 1 | 0.4
524102-00-03 | 259 | 1 | 0.1
524502-00-03 | 259 | 1 | 0.1
572018-00-01 | 259 | 1 | 2.3
572018-00-01 | 259 | 1 | 2.3
255700-00-01 | 259 | 1 | 0.2
255700-00-03 | 259 | 1 | 0.2
274200-01-07 | 259 | 1 | 0.5
322201-00-01 | 259 | 1 | 0.1
334400-00-01 | 259 | 1 | 0.1
334400-00-01 | 259 | 1 | 0.1
334400-00-01 | 259 | 1 | 0.1
334400-01-01 | 259 | 1 | 0.1
334400-01-01 | 259 | 1 | 0.1
334500-00-01 | 259 | 1 | 0.1
062701-00-01 | 296 | 1 | 0.1
062701-00-01 | 296 | 1 | 0.1
212300-01-04 | 296 | 1 | 1
212600-00-06 | 296 | 1 | 0.2
212630-00-03 | 296 | 1 | 0.3
212900-00-02 | 296 | 1 | 0.1
215000-00-02 | 296 | 1 | 2.1
221100-02-01 | 296 | 1 | 0.1
237100-01-02 | 296 | 1 | 0.1
251101-00-05 | 296 | 1 | 0.2
271100-00-09 | 296 | 1 | 0.4
271100-00-09 | 296 | 1 | 0.4
271300-00-01 | 296 | 1 | 0.6
272100-00-03 | 296 | 1 | 0.2
272100-00-09 | 296 | 1 | 1.9
272300-00-01 | 296 | 1 | 0.6
272300-00-03 | 296 | 2 | 0.1
273300-00-01 | 296 | 1 | 0.6
275200-00-01 | 296 | 1 | 0.1
275300-00-09 | 296 | 1 | 1.5
275300-00-09 | 296 | 1 | 1.5
281500-12-01 | 296 | 2 | 0.3
304100-00-01 | 296 | 1 | 0.3
304300-00-01 | 296 | 1 | 0.2
313100-01-04 | 296 | 1 | 0.2
323300-00-02 | 296 | 1 | 0.7
344300-00-01 | 296 | 1 | 0.1
360000-01-18 | 296 | 1 | 0.4
360000-01-18 | 296 | 1 | 0.4
360000-01-19 | 296 | 1 | 0.4
360000-01-19 | 296 | 1 | 0.4
491000-03-02 | 296 | 1 | 0.4
521103-02-09 | 296 | 1 | 0.1
525100-00-01 | 296 | 1 | 0.3
525100-00-02 | 296 | 1 | 0.1
525110-00-01 | 296 | 2 | 0.2
711000-00-01 | 296 | 1 | 0.4
711000-00-01 | 296 | 1 | 0.4
730000-00-07 | 296 | 1 | 1
753200-00-03 | 296 | 1 | 1.1
753200-00-03 | 296 | 1 | 1.1
774600-00-01 | 296 | 1 | 0.1
213100-50-01 | 296 | 1 | 0.3
273500-03-07 | 296 | 1 | 0.2
322100-00-09 | 296 | 1 | 0.1
323300-00-01 | 296 | 1 | 0.3
321100-01-09 | 296 | 1 | 0.1
321100-01-09 | 296 | 1 | 0.1
323200-50-01 | 296 | 1 | 0.1
323200-50-01 | 296 | 1 | 0.1
274300-00-01 | 333 | 1 | 0.5
274300-01-05 | 333 | 1 | 0.6
360000-50-02 | 333 | 1 | 0.9
360000-50-02 | 333 | 1 | 0.9
324200-00-05 | 333 | 2 | 3
212700-00-01 | 333 | 1 | 0.5
262400-00-02 | 333 | 1 | 0.2
335000-02-04 | 333 | 1 | 0.5
342200-00-01 | 333 | 1 | 0.5
341100-50-01 | 333 | 1 | 0.1
300000-50-01 | 333 | 1 | 2.2
300000-50-01 | 333 | 1 | 0.9
300000-50-01 | 333 | 1 | 0.9
062102-00-01 | 370 | 1 | 0.9
062104-00-01 | 370 | 1 | 0.2
062107-00-01 | 370 | 1 | 0.6
062111-00-01 | 370 | 1 | 0.5
062201-00-01 | 370 | 1 | 0.3
062301-00-01 | 370 | 1 | 0.4
062305-00-01 | 370 | 1 | 0.8
062307-00-01 | 370 | 1 | 13.2
062308-00-01 | 370 | 1 | 4.1
062401-00-02 | 370 | 1 | 2.5
062401-00-02 | 370 | 1 | 2.6
062404-00-01 | 370 | 1 | 0.3
062404-00-01 | 370 | 1 | 0.3
062404-00-02 | 370 | 1 | 1.2
062404-00-02 | 370 | 1 | 1.2
062502-00-01 | 370 | 1 | 0.2
062505-00-01 | 370 | 1 | 13
062506-00-01 | 370 | 1 | 9.3
062507-00-01 | 370 | 1 | 10.1
062508-00-01 | 370 | 1 | 0.1
062602-00-01 | 370 | 1 | 0.2
062605-00-01 | 370 | 1 | 13
062606-00-01 | 370 | 1 | 9.3
062607-00-01 | 370 | 1 | 10.1
062608-00-01 | 370 | 1 | 0.1
062702-00-01 | 370 | 1 | 0.1
062801-00-01 | 370 | 1 | 0.4
062901-00-01 | 370 | 1 | 0.5
202107-00-01 | 370 | 1 | 0.4
202111-00-01 | 370 | 1 | 0.5
202403-00-01 | 370 | 1 | 0.5
202403-00-01 | 370 | 1 | 0.5
202701-00-01 | 370 | 1 | 0.1
202701-00-01 | 370 | 1 | 0.1
202901-00-01 | 370 | 1 | 0.1
212300-00-01 | 370 | 1 | 0.3
212300-00-03 | 370 | 1 | 4
212600-00-04 | 370 | 1 | 0.2
212630-01-02 | 370 | 1 | 0.1
213000-00-01 | 370 | 1 | 0.4
213000-00-07 | 370 | 1 | 0.1
221100-00-02 | 370 | 1 | 0.2
221100-00-02 | 370 | 1 | 0.3
221100-00-02 | 370 | 1 | 0.4
222100-00-01 | 370 | 1 | 0.4
243000-00-02 | 370 | 1 | 0.1
243000-00-06 | 370 | 1 | 0.3
243000-00-06 | 370 | 1 | 0.1
251101-00-03 | 370 | 1 | 0.1
251101-00-04 | 370 | 1 | 0.1
251104-00-02 | 370 | 1 | 0.1
251104-00-03 | 370 | 1 | 0.1
252101-00-03 | 370 | 1 | 1.7
252101-00-04 | 370 | 1 | 0.3
252103-00-02 | 370 | 1 | 0.1
252103-00-03 | 370 | 1 | 0.1
253110-00-01 | 370 | 1 | 0.2
261100-00-02 | 370 | 1 | 0.1
261200-00-02 | 370 | 1 | 0.1
262200-00-04 | 370 | 1 | 0.2
270001-00-02 | 370 | 1 | 2.7
270001-00-02 | 370 | 1 | 2.7
270001-00-05 | 370 | 1 | 2.6
270001-00-05 | 370 | 1 | 2.6
270001-00-07 | 370 | 1 | 0.2
270100-00-01 | 370 | 1 | 0.5
271100-00-08 | 370 | 2 | 0.8
271100-00-14 | 370 | 1 | 0.3
271100-00-18 | 370 | 1 | 2.4
271100-00-18 | 370 | 1 | 2.4
271100-00-19 | 370 | 1 | 0.3
271100-00-20 | 370 | 1 | 1.7
271100-00-20 | 370 | 1 | 1.7
272300-00-04 | 370 | 2 | 0.3
273100-00-02 | 370 | 1 | 0.6
273100-00-09 | 370 | 1 | 1
273500-00-02 | 370 | 1 | 0.3
274100-00-07 | 370 | 1 | 0.4
274200-00-02 | 370 | 1 | 1.2
274300-00-03 | 370 | 1 | 0.4
274400-00-01 | 370 | 1 | 0.1
274500-00-02 | 370 | 1 | 0.1
275100-00-01 | 370 | 1 | 0.2
275300-00-01 | 370 | 1 | 0.4
275300-00-10 | 370 | 1 | 0.6
275300-00-10 | 370 | 1 | 0.6
275400-00-01 | 370 | 1 | 0.8
276100-00-02 | 370 | 1 | 0.2
276100-00-06 | 370 | 1 | 0.5
276400-00-04 | 370 | 1 | 0.2
276500-00-01 | 370 | 1 | 0.2
277100-00-07 | 370 | 1 | 0.4
282300-00-01 | 370 | 1 | 0.2
291100-00-02 | 370 | 1 | 0.3
291300-00-11 | 370 | 1 | 0.3
293100-00-01 | 370 | 1 | 0.3
301100-00-05 | 370 | 1 | 0.7
301100-02-10 | 370 | 2 | 0.3
301200-00-06 | 370 | 1 | 0.3
302000-00-02 | 370 | 1 | 0.7
302000-00-02 | 370 | 1 | 0.7
302000-00-03 | 370 | 1 | 0.3
302000-00-03 | 370 | 1 | 0.3
304100-01-02 | 370 | 1 | 0.1
313100-00-03 | 370 | 1 | 0.1
315100-00-02 | 370 | 1 | 0.1
320001-00-02 | 370 | 1 | 0.8
320001-00-05 | 370 | 1 | 0.3
321100-00-03 | 370 | 1 | 0.3
321100-00-03 | 370 | 1 | 0.3
322100-00-03 | 370 | 1 | 0.3
322201-00-02 | 370 | 1 | 0.2
323200-00-04 | 370 | 1 | 0.2
323300-00-04 | 370 | 1 | 0.2
324300-00-04 | 370 | 1 | 0.4
324400-00-01 | 370 | 1 | 0.1
324400-00-03 | 370 | 1 | 0.2
324500-01-05 | 370 | 1 | 0.3
324800-00-01 | 370 | 1 | 0.1
325100-00-05 | 370 | 2 | 2.1
325200-00-01 | 370 | 1 | 0.3
325200-00-02 | 370 | 1 | 0.2
344300-01-01 | 370 | 1 | 0.2
360000-00-01 | 370 | 1 | 0.9
360000-00-01 | 370 | 1 | 0.9
360000-00-03 | 370 | 1 | 1.4
360000-00-03 | 370 | 1 | 1.4
360000-00-05 | 370 | 2 | 0.7
360000-00-06 | 370 | 2 | 1
360000-00-06 | 370 | 2 | 1
360000-00-07 | 370 | 1 | 0.4
360000-00-08 | 370 | 2 | 0.4
360000-04-21 | 370 | 1 | 0.3
491000-00-01 | 370 | 1 | 0.3
495200-00-01 | 370 | 1 | 0.2
498000-00-02 | 370 | 1 | 0.4
521102-00-10 | 370 | 1 | 0.4
521103-00-07 | 370 | 1 | 0.3
521104-00-01 | 370 | 1 | 0.3
521202-00-05 | 370 | 1 | 0.2
522102-00-02 | 370 | 1 | 0.3
523002-00-01 | 370 | 1 | 1.3
523002-00-02 | 370 | 1 | 0.5
523300-00-05 | 370 | 1 | 0.5
524102-00-06 | 370 | 1 | 0.2
524301-00-01 | 370 | 1 | 0.2
524302-00-03 | 370 | 1 | 0.2
524502-00-06 | 370 | 1 | 0.1
527100-00-01 | 370 | 2 | 0.3
531404-00-01 | 370 | 1 | 0.3
531405-00-04 | 370 | 1 | 0.3
562000-00-01 | 370 | 1 | 0.5
712103-00-02 | 370 | 1 | 0.2
712103-00-02 | 370 | 1 | 0.2
761100-00-10 | 370 | 1 | 1
762300-00-03 | 370 | 1 | 0.2
762300-00-03 | 370 | 1 | 0.2
524154-00-01 | 370 | 1 | 0.2
524155-00-01 | 370 | 1 | 0.2
524554-00-01 | 370 | 1 | 0.1
524555-00-01 | 370 | 1 | 0.1
531001-00-08 | 370 | 1 | 0.2
531029-00-01 | 370 | 1 | 0.1
533025-00-01 | 370 | 1 | 0.9
533025-01-01 | 370 | 1 | 0.9
534301-00-02 | 370 | 1 | 0.2
572018-01-01 | 370 | 1 | 2.3
572018-01-01 | 370 | 1 | 2.3
572032-00-01 | 370 | 1 | 0.2
572032-00-01 | 370 | 1 | 0.2
221100-00-04 | 370 | 1 | 0.1
221100-00-04 | 370 | 1 | 1.1
222100-00-03 | 370 | 1 | 0.9
222100-00-08 | 370 | 1 | 0.2
271100-00-02 | 370 | 1 | 0.1
271100-00-03 | 370 | 1 | 0.3
271100-00-04 | 370 | 1 | 0.4
271100-00-04 | 370 | 1 | 0.4
271100-00-05 | 370 | 1 | 0.1
271100-00-07 | 370 | 1 | 3.6
271100-00-07 | 370 | 1 | 3.6
271400-00-01 | 370 | 1 | 0.2
272100-00-01 | 370 | 1 | 0.4
272100-00-02 | 370 | 1 | 0.4
272200-00-01 | 370 | 1 | 1
272400-00-01 | 370 | 1 | 1.6
273100-00-01 | 370 | 1 | 0.4
273100-00-03 | 370 | 1 | 1
273100-00-05 | 370 | 1 | 2.3
275001-00-02 | 370 | 1 | 0.7
275001-00-02 | 370 | 1 | 0.7
275300-00-03 | 370 | 1 | 0.1
275300-00-03 | 370 | 1 | 0.5
275300-00-03 | 370 | 1 | 0.5
276100-00-01 | 370 | 1 | 0.3
276400-00-08 | 370 | 3 | 1.4
276400-00-08 | 370 | 3 | 1.4
277100-00-02 | 370 | 1 | 0.1
277100-00-03 | 370 | 1 | 0.4
325100-00-01 | 370 | 1 | 0.1
521202-00-02 | 370 | 1 | 0.2
522102-00-01 | 370 | 1 | 0.3
523002-00-03 | 370 | 1 | 0.3
523300-00-01 | 370 | 1 | 0.2
523300-00-07 | 370 | 1 | 0.5
523300-02-07 | 370 | 1 | 0.4
524102-00-02 | 370 | 1 | 0.2
524302-00-01 | 370 | 1 | 0.2
524502-00-02 | 370 | 1 | 0.3
531405-00-01 | 370 | 1 | 0.3
561000-00-01 | 370 | 1 | 0.2
062305-00-02 | 444 | 1 | 0.2
212700-00-02 | 444 | 1 | 0.2
221100-00-06 | 444 | 1 | 0.3
236000-00-01 | 444 | 1 | 1
236000-00-01 | 444 | 1 | 1
236000-00-01 | 444 | 1 | 1
243000-00-05 | 444 | 1 | 0.5
261301-00-03 | 444 | 1 | 1.1
261301-00-04 | 444 | 1 | 0.3
261303-01-02 | 444 | 1 | 0.4
262100-00-05 | 444 | 1 | 0.2
274100-01-06 | 444 | 1 | 1.2
274200-00-01 | 444 | 1 | 1.1
275300-00-06 | 444 | 1 | 1.3
275300-00-06 | 444 | 1 | 1.3
303100-00-01 | 444 | 1 | 0.2
303100-00-02 | 444 | 1 | 0.1
304100-00-03 | 444 | 1 | 0.4
323300-00-05 | 444 | 1 | 0.3
323300-00-05 | 444 | 1 | 0.3
341100-00-01 | 444 | 1 | 0.2
341100-01-01 | 444 | 1 | 0.5
341100-02-04 | 444 | 1 | 2.5
341100-02-05 | 444 | 1 | 0.5
341200-00-02 | 444 | 1 | 0.5
521202-00-01 | 444 | 1 | 0.3
521202-00-06 | 444 | 1 | 0.2
523300-00-04 | 444 | 1 | 0.5
523300-02-04 | 444 | 1 | 0.5
574000-00-02 | 444 | 1 | 0.3
574000-00-02 | 444 | 1 | 0.3
761100-00-05 | 444 | 1 | 0.3
773100-00-02 | 444 | 1 | 0.3
774100-00-01 | 444 | 1 | 0.2
521253-00-01 | 444 | 1 | 0.1
533009-00-03 | 444 | 1 | 0.3
274100-00-01 | 444 | 1 | 0.6
323100-00-01 | 444 | 1 | 1
324300-00-01 | 444 | 1 | 0.1
215000-50-01 | 444 | 1 | 3.9
801000-00-01 | 444 | 1 | 0.3
801000-00-01 | 444 | 1 | 0.3
321100-00-05 | 444 | 1 | 0.1
321100-00-05 | 444 | 1 | 0.1
335000-00-02 | 518 | 1 | 0.9
335000-01-02 | 518 | 1 | 1
321100-00-04 | 518 | 1 | 0.2
321100-00-04 | 518 | 1 | 0.2
321100-01-04 | 518 | 1 | 0.2
321100-01-04 | 518 | 1 | 0.2
322100-00-04 | 518 | 1 | 0.2
322100-00-05 | 518 | 1 | 0.1
323200-00-01 | 518 | 1 | 0.3
323200-01-05 | 518 | 1 | 0.2
521105-00-01 | 518 | 1 | 0.1
262500-01-05 | 518 | 1 | 0.4
062105-00-01 | 518 | 1 | 2.2
212700-00-03 | 518 | 1 | 0.1
281600-12-01 | 518 | 1 | 0.2
281600-12-02 | 518 | 1 | 0.2
574000-00-01 | 518 | 1 | 0.1
574000-00-01 | 518 | 1 | 0.1
241000-50-01 | 518 | 1 | 3.1
241000-50-01 | 518 | 1 | 3.1
723010-00-03 | 518 | 1 | 0.1
723010-00-03 | 518 | 1 | 0.1
533013-00-04 | 666 | 1 | 0.3
533014-00-04 | 666 | 1 | 0.3
712103-00-01 | 666 | 1 | 0.7
712103-00-01 | 666 | 1 | 0.7
360000-06-23 | 666 | 1 | 0.4
533003-00-04 | 703 | 1 | 0.2
544000-00-01 | 703 | 1 | 1.3
544000-00-01 | 703 | 1 | 1.3
062101-00-01 | 740 | 1 | 0.2
062101-00-02 | 740 | 1 | 0.6
062103-00-01 | 740 | 1 | 0.6
062108-00-01 | 740 | 1 | 0.6
062108-20-02 | 740 | 1 | 0.4
062202-20-01 | 740 | 1 | 0.8
062203-20-01 | 740 | 1 | 0.3
062204-00-01 | 740 | 1 | 0.4
062302-00-01 | 740 | 1 | 0.3
062303-00-01 | 740 | 1 | 0.3
062401-00-01 | 740 | 1 | 0.3
062401-00-01 | 740 | 1 | 0.3
202103-00-01 | 740 | 1 | 0.4
202107-00-03 | 740 | 1 | 0.4
202108-00-01 | 740 | 1 | 0.8
202108-00-02 | 740 | 1 | 0.2
202108-00-03 | 740 | 1 | 0.8
202108-00-04 | 740 | 1 | 0.2
202202-00-01 | 740 | 1 | 0.4
202202-00-02 | 740 | 1 | 0.5
202203-00-01 | 740 | 1 | 0.3
202204-00-01 | 740 | 1 | 0.2
202505-00-01 | 740 | 1 | 1.3
202605-00-01 | 740 | 1 | 1.3
202901-00-02 | 740 | 1 | 0.1
213000-00-03 | 740 | 1 | 0.2
213000-00-06 | 740 | 1 | 0.3
221100-00-03 | 740 | 1 | 0.4
222100-00-02 | 740 | 1 | 0.2
222100-00-04 | 740 | 1 | 0.9
223100-00-01 | 740 | 1 | 0.2
223100-00-02 | 740 | 1 | 0.2
233100-00-02 | 740 | 2 | 0.4
255700-00-04 | 740 | 1 | 0.2
255700-00-05 | 740 | 1 | 0.3
255700-00-06 | 740 | 1 | 0.2
261301-00-02 | 740 | 1 | 0.3
261303-00-02 | 740 | 1 | 0.2
261303-00-04 | 740 | 1 | 0.3
262500-00-05 | 740 | 1 | 0.4
270001-00-03 | 740 | 1 | 3.9
270001-00-06 | 740 | 1 | 3.6
271100-00-06 | 740 | 1 | 0.3
273500-03-05 | 740 | 1 | 0.2
274200-00-04 | 740 | 1 | 1.3
274200-01-12 | 740 | 1 | 0.1
276400-00-01 | 740 | 1 | 0.3
282200-00-01 | 740 | 1 | 2.3
284300-00-01 | 740 | 1 | 0.1
290100-00-02 | 740 | 1 | 0.1
291300-00-02 | 740 | 2 | 3.1
303100-01-01 | 740 | 1 | 0.1
303100-01-02 | 740 | 1 | 0.1
323100-00-02 | 740 | 1 | 0.2
323300-00-03 | 740 | 1 | 0.3
324400-00-02 | 740 | 1 | 0.3
324400-00-05 | 740 | 1 | 0.4
324500-00-01 | 740 | 1 | 0.3
341100-00-04 | 740 | 1 | 2.5
341200-00-01 | 740 | 1 | 0.1
360000-00-02 | 740 | 1 | 0.2
360000-00-02 | 740 | 1 | 0.7
360000-00-04 | 740 | 1 | 0.7
381200-00-02 | 740 | 1 | 0.3
521203-00-02 | 740 | 1 | 0.2
523002-00-04 | 740 | 1 | 0.2
523300-00-08 | 740 | 1 | 0.2
524102-00-01 | 740 | 1 | 0.2
524104-00-02 | 740 | 1 | 0.2
524502-00-01 | 740 | 1 | 0.3
524504-00-02 | 740 | 1 | 0.3
730000-00-05 | 740 | 1 | 0.3
761100-00-04 | 740 | 1 | 0.3
761100-00-09 | 740 | 1 | 0.3
761300-00-02 | 740 | 1 | 0.3
761300-00-06 | 740 | 1 | 0.3
783500-02-01 | 740 | 2 | 0.4
524153-00-01 | 740 | 1 | 0.3
524553-00-01 | 740 | 1 | 0.2
531023-00-01 | 740 | 1 | 0.1
534201-00-02 | 740 | 1 | 0.3
571014-00-01 | 740 | 1 | 0.2
577101-00-02 | 740 | 1 | 0.1
577101-00-02 | 740 | 1 | 0.1
321100-01-17 | 740 | 1 | 0.1
321100-01-17 | 740 | 1 | 0.1
221100-00-07 | 888 | 1 | 0.8
251101-00-01 | 888 | 1 | 0.2
252101-00-02 | 888 | 1 | 3.3
252103-00-01 | 888 | 1 | 0.3
274200-01-01 | 888 | 1 | 0.5
275200-00-02 | 888 | 1 | 0.3
276400-00-06 | 888 | 1 | 0.2
281600-12-03 | 888 | 2 | 1.2
293700-00-01 | 888 | 1 | 0.4
301100-00-08 | 888 | 1 | 0.4
301200-00-08 | 888 | 2 | 1.2
323100-00-04 | 888 | 1 | 1.9
323100-00-05 | 888 | 1 | 1.8
324300-00-06 | 888 | 1 | 0.3
360000-00-11 | 888 | 1 | 0.4
360000-01-16 | 888 | 1 | 1.1
360000-01-16 | 888 | 1 | 1.1
360000-01-17 | 888 | 1 | 0.8
360000-01-17 | 888 | 1 | 0.8
783100-00-04 | 888 | 1 | 1.7
783100-00-04 | 888 | 1 | 1.7
783100-00-05 | 888 | 2 | 1.6
783100-00-05 | 888 | 2 | 1.6
783200-01-03 | 888 | 2 | 0.2
783200-01-03 | 888 | 2 | 0.2
534202-00-02 | 888 | 1 | 0.4
534203-00-02 | 888 | 1 | 0.4
360000-50-01 | 888 | 1 | 0.6
360000-50-01 | 888 | 1 | 0.6
276400-00-02 | 888 | 1 | 1.1
521102-00-09 | 999 | 2 | 0.2
801000-00-02 | 999 | 1 | 0.4
801000-00-02 | 999 | 1 | 0.4
531019-00-05 | 999 | 1 | 0.3
062501-00-01 | 999 | 1 | 0.6
062601-00-01 | 999 | 1 | 0.6
521203-00-03 | 999 | 1 | 0.3
523053-00-01 | 999 | 1 | 0.3
523053-00-03 | 999 | 1 | 0.1
572004-60-05 | 999 | 1 | 0.2
572004-60-05 | 999 | 1 | 0.2
575502-00-01 | 999 | 1 | 0.3
575502-00-01 | 999 | 1 | 0.3
575602-00-01 | 999 | 1 | 0.3
575602-00-01 | 999 | 1 | 0.3
240000-50-01 | 999 | 1 | 0.1
062106-00-01 | 1110 | 1 | 0.3
062107-00-02 | 1110 | 1 | 0.4
062109-00-01 | 1110 | 1 | 1.2
062109-01-01 | 1110 | 1 | 0.4
062113-00-01 | 1110 | 1 | 2.3
062202-20-02 | 1110 | 1 | 0.1
062203-20-02 | 1110 | 1 | 0.2
062205-20-01 | 1110 | 1 | 0.4
062503-20-01 | 1110 | 1 | 3
062603-20-01 | 1110 | 1 | 3
062603-20-02 | 1110 | 1 | 2.8
202103-00-02 | 1110 | 2 | 0.4
202103-00-03 | 1110 | 1 | 0.4
202106-00-01 | 1110 | 1 | 0.6
202107-00-02 | 1110 | 1 | 0.2
202107-00-04 | 1110 | 1 | 0.2
202109-00-01 | 1110 | 1 | 0.4
202109-00-02 | 1110 | 1 | 0.4
202109-01-01 | 1110 | 1 | 0.4
202109-01-02 | 1110 | 1 | 0.4
202202-00-03 | 1110 | 1 | 0.1
202202-00-04 | 1110 | 1 | 0.1
202202-00-05 | 1110 | 1 | 0.1
202203-00-03 | 1110 | 1 | 0.2
202204-00-02 | 1110 | 1 | 0.2
202205-00-01 | 1110 | 1 | 0.2
202205-00-02 | 1110 | 1 | 0.2
202307-00-01 | 1110 | 1 | 1
202308-00-01 | 1110 | 1 | 1.8
202503-00-02 | 1110 | 1 | 3
202603-00-02 | 1110 | 1 | 3
202603-00-03 | 1110 | 1 | 2.8
212000-00-01 | 1110 | 1 | 1.1
212600-00-05 | 1110 | 1 | 0.9
212800-00-01 | 1110 | 1 | 0.4
213000-00-02 | 1110 | 1 | 0.3
213000-00-05 | 1110 | 1 | 0.1
215000-00-05 | 1110 | 1 | 0.3
215000-00-06 | 1110 | 1 | 0.8
215000-00-07 | 1110 | 1 | 0.8
222100-00-06 | 1110 | 1 | 0.3
236000-00-02 | 1110 | 1 | 0.6
236000-00-02 | 1110 | 1 | 4.2
236000-00-02 | 1110 | 1 | 0.5
236000-00-02 | 1110 | 1 | 0.5
236000-00-02 | 1110 | 1 | 0.3
236000-00-02 | 1110 | 1 | 0.3
236000-00-02 | 1110 | 1 | 0.9
236000-00-02 | 1110 | 1 | 0.3
251104-00-01 | 1110 | 1 | 0.2
252101-00-01 | 1110 | 1 | 1.7
270001-00-01 | 1110 | 1 | 3
270001-00-04 | 1110 | 1 | 3
271400-00-03 | 1110 | 1 | 0.3
273500-00-04 | 1110 | 1 | 0.4
274100-02-07 | 1110 | 1 | 0.8
274200-01-09 | 1110 | 1 | 0.7
274200-01-10 | 1110 | 1 | 1.5
274200-01-11 | 1110 | 1 | 0.4
274400-01-03 | 1110 | 1 | 0.6
274400-01-04 | 1110 | 1 | 0.5
274500-00-01 | 1110 | 1 | 0.6
275100-00-02 | 1110 | 1 | 0.3
275300-00-02 | 1110 | 1 | 0.7
275300-00-11 | 1110 | 1 | 0.9
275300-00-11 | 1110 | 1 | 0.9
277100-00-01 | 1110 | 2 | 0.6
293200-00-01 | 1110 | 1 | 0.6
293500-00-01 | 1110 | 1 | 0.6
301100-00-02 | 1110 | 1 | 2.8
301100-00-02 | 1110 | 1 | 2.8
301100-00-03 | 1110 | 1 | 0.5
301100-00-03 | 1110 | 1 | 0.5
301100-00-06 | 1110 | 1 | 0.2
301100-00-07 | 1110 | 1 | 0.4
301100-00-09 | 1110 | 1 | 6.2
301100-00-09 | 1110 | 1 | 6.2
301200-00-02 | 1110 | 1 | 4.4
301200-00-03 | 1110 | 1 | 4.3
301200-00-07 | 1110 | 1 | 0.2
301200-00-11 | 1110 | 1 | 1.2
301200-01-08 | 1110 | 2 | 1.2
320001-00-01 | 1110 | 1 | 0.5
320001-00-04 | 1110 | 1 | 0.5
324300-00-03 | 1110 | 1 | 0.3
324300-00-05 | 1110 | 1 | 0.2
360000-00-09 | 1110 | 1 | 0.3
360000-00-12 | 1110 | 1 | 0.8
360000-00-14 | 1110 | 1 | 0.5
495100-00-01 | 1110 | 1 | 0.1
521103-00-04 | 1110 | 1 | 0.2
521202-00-04 | 1110 | 1 | 0.2
524102-00-05 | 1110 | 1 | 0.4
524502-00-05 | 1110 | 1 | 0.4
761100-00-03 | 1110 | 1 | 0.3
761100-00-08 | 1110 | 1 | 0.6
761300-00-01 | 1110 | 1 | 0.3
761300-00-05 | 1110 | 1 | 5.1
783200-00-02 | 1110 | 1 | 0.4
535001-00-02 | 1110 | 1 | 0.4
271100-00-01 | 1110 | 1 | 0.1
272100-00-10 | 1110 | 1 | 0.2
062402-00-01 | 1110 | 1 | 0.2
062402-00-01 | 1110 | 1 | 0.2
323200-00-06 | 1110 | 1 | 1
323200-00-06 | 1110 | 1 | 1
352100-00-01 | 1443 | 1 | 2
524104-00-03 | 1443 | 1 | 0.3
524504-00-03 | 1443 | 1 | 0.3
521154-00-01 | 1443 | 1 | 0.2
531011-00-01 | 1443 | 1 | 0.2
533010-00-01 | 1443 | 1 | 0.5
533026-00-01 | 1443 | 1 | 0.1
533026-01-01 | 1443 | 1 | 0.1
533030-00-01 | 1443 | 1 | 0.5
534124-00-01 | 1443 | 1 | 0.3
534128-00-01 | 1443 | 1 | 0.3
534204-60-01 | 1443 | 1 | 0.1
535001-00-01 | 1443 | 1 | 0.4
572015-00-01 | 1443 | 1 | 3.2
572015-00-01 | 1443 | 1 | 3.2
322100-00-07 | 1443 | 1 | 0.1
492000-00-01 | 1443 | 1 | 0.2
215000-00-10 | 1443 | 1 | 3
499000-00-03 | 1776 | 1 | 0.6
262100-00-02 | 1776 | 1 | 0.9
262100-00-04 | 1776 | 1 | 2
262200-00-02 | 1776 | 1 | 0.6
262200-00-06 | 1776 | 1 | 0.3
262400-00-04 | 1776 | 1 | 0.1
262500-00-02 | 1776 | 1 | 1
262500-01-02 | 1776 | 1 | 1
494000-00-01 | 1998 | 1 | 0.4